## Sheet1
Phase 1: Foundation & Core Setup
1. Django Project Setup
Create main project structure | Done
Configure settings for bilingual support (English/Swahili) | Not yet to be done when coding begins
Set up security configurations (no session tracking for anonymous users) | Done,
Configure database models | Will be done later
2. Core Models
Report Model: Store anonymous reports with optional fields | Done, on models.py of report
VoiceReport Model: Handle audio file uploads | Done
AdminProfile Model: Extend User model with role assignments | Done but some things can be added later
HelpResource Model: Store support information and helplines | Done
AuditLog Model: Track all admin actions | Done but some things can be added later
3. Authentication System
Custom admin authentication (NO regular user auth) | Done
Role-based permission groups | Done
Admin role assignment system | Done
Phase 2: Public/Anonymous User Pages